## Test Case
Product Name | https://bionstyle.com/ | TC Start Date | 2023-11-01 | Test Case Execution Start Date | 2023-11-01 |  |  | Test Cases
Module Name | Sign Up, Login and Place Order | TC End Date | 16/01/2023 | Test Case Execution End Date | 16/01/2023 |  |  | Pass | 49
Epic |  | Test Case Developed By | Nusrat Jahan Mou | Browser(tested) | Yes |  |  | Fail | 3
Developer Name | Ponkoj Biswas | Test Case Reviewed by |  | Performance(tested) | Yes |  |  | Out Of Scope | 0
Test Executed By | Nusrat Jahan Mou | [6 empty] | Not Executed | 0
[8 empty] | Total | 52
#SL No | Module | Type of Testing | Features | Test Case | Expected Result | Actual Result | Test Data | Reproducing Steps | Bug Screenshot | Dev Comments | Final Result
BS-001 |  | Browser Compatibility Testing |  | Verify whether the website runs on all browsers or not | Should run on all browsers | Found as expected | 1. Google Chrome 2. Microsoft Edge | 1. Open different browsers 2. Open the URL of the website on different browsers |  |  | Passed
BS-002 | User Management | UI testing | Sign Up | Check if there is any grammatical or spelling mistakes or not | There should not be any grammatical mistake | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Then click register 4. Check for any grammatical or spelling mistake |  |  | Passed
BS-003 |  |  |  | Check font size,text color are accurate or not | Should meet the client's requirement | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Then click register 4. Check whether font size, text color are accurate or not |  |  | Passed
BS-004 |  |  |  | Check if there is any red astrick beside mandatory fields or not | Red Astrick should be present | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on register 4. Check for red astrick beside mandatory fields |  |  | Passed
BS-005 |  |  |  | Verify whether hover works or not | Hover should work | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on register 4. Hover over fields |  |  | Passed
BS-006 |  |  |  | Check if alignment is proper or not | Fields should be aligned properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on register 4. Check if fields are aligned properly or not |  |  | Passed
BS-007 |  |  |  | Checking if scrollbars according to the size of the page if any | Scrollbars should work properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on register 4. Check if scrollbar works or not |  |  | Passed
Name: Nusrat Jahan Mou
BS-008 |  |  |  | Checking whether size of the image is accurate or not | Should meet the client's requirement | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on register 4. Check every image's size accuracy |  |  | Passed
BS-009 | User Management | UI Testing | Login | Checking if there is any grammatical or spelling mistakes or not | There should not be any grammatical mistake | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Then click login 4. Check for any grammatical or spelling mistake |  |  | Passed
BS-010 |  |  |  | Check font size,text color are accurate or not | Should meet the client's requirement | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Then click login 4. Check whether font size, text color are accurate or not |  |  | Passed
BS-011 |  |  |  | Check if there is any red astrick beside mandatory fields or not | There should be red astrick beside mandatory fields | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on login 4. Check for red astrick beside mandatory fields |  |  | Passed
BS-012 |  |  |  | Check for placeholders in every field | There should be placeholders in necessary fields | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on login 4. Check for placeholders |  |  | Passed
BS-013 |  |  |  | Check if remember me button works or not | Should be working properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on login 4. Check remember me button |  |  | Passed
BS-014 |  |  |  | Verify whether hover works or not | Hover should work | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on login 4. Hover over fields |  |  | Passed
BS-015 |  |  |  | Check if alignment is proper or not | Fields should be aligned properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on login 4. Check if fields are aligned properly or not |  |  | Passed
BS-016 | User Management | Functional Testing | Sign Up | Keeping the mandatory fields blank | Should not allow to register and show an error message | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on "My Account" 3. Click on register 4. Keep the mandatory fields blank and Click on 'Create Account' 5. Check if user can register keeping the mandatory fields or not |  |  | Passed
BS-017 |  |  |  | Fill Out all the necessary fields with valid information | Should allow user to register | Found as expected | Name : Nurun Nahar Begum Phone : 01720970244 Email : nbegum.ammu@gmail.com Password: mkii_106# Confirm Password: mkii_106# | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out all necessary fields with valid information 5. Click 'Create Account' |  |  | Passed
BS-018 |  |  |  | Fill out only the name field and keep other fields blank | Should not allow user to register and show an error message | Found as expected | Name : Nusrat Jahan Mou Phone : Email : Password: Confirm Password: | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out only the name field keeping the other fields blank 5. Click 'Create Account' |  |  | Passed
BS-019 |  |  |  | Fill out only the phone number field and keep other fields blank | Should not allow user to register and show an error message | Found as expected | Name : Phone : 01763516486 Email : Password: Confirm Password: | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out only the phone number field keeping the other fields blank 5. Click 'Create Account' |  |  | Passed
BS-020 |  |  |  | Fill out only the email field and keep other fields blank | Should not allow user to register and show an error message | Found as expected | Name : Phone : Email : nus.mou.106@gmail.com Password: Confirm Password: | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out only the email field keeping the other fields blank 5. Click 'Create Account' |  |  | Passed
BS-021 |  |  |  | Fill out only the password field and keep other fields blank | Should not allow user to register and show an error message | Found as expected | Name : Phone : Email : Password: jhki_106# Confirm Password: | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out only the password field keeping the other fields blank 5. Click 'Create Account |  |  | Passed
BS-022 |  |  |  | Fill out only the confirm password field and keep other fields blank | Should not allow user to register and show an error message | Found as expected | Name : Phone : Email : Password: Confirm Password: jhki_106# | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out only the confirm password field keeping the other fields blank 5. Click 'Create Account |  |  | Passed
BS-023 |  |  |  | Fill out phone number field with alphanumric characters | User should not able to enter alphanumeric character in the phone number field | Found as expected | phone number: abcd01876 | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Enter alphanumeric characters in the phone number field |  |  | Passed
BS-024 |  |  |  | Fill out email field with invalid email address | Should show an error message | Found as expected | email: nusmougmail.com | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out email field with invalid email address |  |  | Passed
BS-025 |  |  |  | Enter a phone number less than 11 digits | Should show an error message | Found as expected | phone number: 01763415 | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Enter a phone number with less than 11 digits |  |  | Passed
BS026 |  |  |  | Enter a password less than 6 characters | Show an error message | Found as expected | Password: 111 | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Enter a password with less than 6 characters |  |  | Passed
BS-027 |  |  |  | Enter a weak password without any special characters | Should show an error message | Not found as expected | Password: 123456 | 1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Enter a weak password with no special characters. 5. Click 'Create Account' |  |  | Failed
BS-028 |  |  |  | Check if confirm password field matches with the password field or not | Confirm password must match with previously entered password | Found as expected | Password: vgtx@107 Confirm Password: jhdjhDFA | """1. Go To URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Enter a password in the confirm password field that does not match with the previously entered password" 5. Click Create Account |  |  | Passed
BS-029 |  |  |  | Check if user can register can sign up with an existing account or not | User should not be able to register with an existing email and phone number | Found as expected | "Name : Nusrat Jahan Mou Phone : 01763516486 Email : nus.mou.106@gmail.com Password: jhki_106# Confirm Password: jhki_106#" | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on register 4. Fill out all the necessary fields with already existing information 5. Click 'Create Account' |  |  | Passed
BS-030 | User Management | Functional Testing | Login | Keeping all the mandatory fields blank | Should show an error message | Found as exppected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Keep all the mandatory fields blank 5. Click 'Create Account' |  |  | Passed
BS-031 |  |  |  | Login with valid credential | User should be able to login successfully | Found as expected | Username: nus.mou.106@gmail.com | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Login with valid credential |  |  | Passed
BS-032 |  |  |  | Keeping the username field blank and fill out the password field valid password | User should not be able to register without an username | Found as expected | Username: Password: 123456 | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Keep the username field blank and fill out the password field with valid password |  |  | Passed
BS-033 |  |  |  | Keeping the password field blank and fill out the username field valid username | User should not be able to register without a password | Found as expected | Username: nus.mou.106@gmail.com Password: | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Keep the password field blank and fill out the username field with valid username |  |  | Passed
BS-034 |  |  |  | Enter invalid username and valid password | User should not be able to register | Found as expected | Username: nusmou@gmail.com Password: 123456 | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Enter invalid username and valid password |  |  | Passed
BS--035 |  |  |  | Enter valid username and invalid password | User should not be able to register | Found as expected | Username: nus.mou.106@gmail.com Password: 222222 | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Enter valid username and invalid password |  |  | Passed
BS-036 |  |  |  | Enter invalid username and password | User should not be able to register | Found as expected | Username: nusmo106@gmail.com Password: 222222 | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Enter invalid username and password |  |  | Passed
BS-037 |  |  |  | Check if user can login with the newly registered credential or not | User should be able to register successfully | Found as expected | Username: nbegum.ammu@gmail.com Password: mkii_106# | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Login with newly created ccount credential |  |  | Passed
BS-038 |  |  |  | Check if remember me functionality works properly or not | Should be working properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Click on remember me |  |  | Passed
BS-039 |  |  |  | Verify forgot password functionality | User should be able to change password by providing phone number or email | Not found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Click on forgot password |  |  | Failed
BS-040 |  |  |  | Check if user can add product to cart without logging in or not | User must log in before purchasing anything | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Add a product to cart without logging in |  |  | Passed
BS-041 | Place Order | UI Testing | Cart | Check if there is any grammatical or spelling mistakes or not | There should not be any grammatical mistake | Found as expected | N/A | "1. Go to URL https://bionstyle.com/ 2. Login with valid credential 3. Add a product to the cart 4. View Cart" 5. Check for any grammatical or spelling mistake |  |  | Passed
BS-042 |  |  |  | Check font size,text color are accurate or not | Should be according to client's requirement | Found as expected | N/A | "1. Go to URL https://bionstyle.com/ 2. Login with valid credential 3. Add a product to the cart 4. View Cart" 5. Check for font size, text color |  |  | Passed
BS-043 |  |  |  | Check if there is any red astrick beside mandatory fields or not | Should be red astrick beside mandatory fields | Found as expected | N/A | 1. Go To URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View Cart 5.Check whether red astrick shows beside mandatory fields or not |  |  | Passed
BS-044 |  |  |  | Verify whether hover works or not | Hover should work properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Hover over every fields |  |  | Passed
BS-045 |  |  |  | Check if alignment is proper or not | Should be aligned properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Check alignement of every field |  |  | Passed
BS-046 |  |  |  | Checking if scrollbar is properly working or not | Should be working properly | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Check scrollbar working or not |  |  | Passed
BS-047 | Place Order | Functional Testing | Billing Address | Keep all the mandatory fields blank | Should show an error message | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Keep all the mandatory fields blank |  |  | Passed
BS-048 |  |  |  | Fill out all necessary fields with valid information | User should be able to place order | Found as expected | Name: Nusrat Jahan Phone number: 01763516486 Email: nus.mou.106@gmail.com District: Dhaka Area: Moghbazar Address:4/2 new circular road, Moghbazar, Dhaka | 1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Fill out all the necessary fields with valid information |  |  | Passed
BS-049 |  |  |  | Verifying adding or reducing product from the cart | User should be able to add or reduce product from the cart | Found as expected | N/A | 1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Fill out all the necessary fields with valid information 6. Add or reduce product from the cart |  |  | Passed
BS-050 | Place Order | Functional Testing | Payment | Verifying cash on deliver functionality | User should be able to pay by cash | Found as expected | Select cash on delivery button | "1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Fill out all the necessary fields with valid information 6. Add or reduce product from the cart" 7. In the payment section, select cash on delivery option |  |  | Passed
BS-051 |  |  |  | Verify online payment method | User should be able to pay online | Not found as expected | Select online payment option | "1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Fill out all the necessary fields with valid information 6. Add or reduce product from the cart" 7. In the payment section, select pay online option |  |  | Failed
BS-052 |  |  |  | Verify discount by coupon functionality | User should be able to avail discount by providing a coupon code | Found as expected | bion123 | """1. Go to URL https://bionstyle.com/ 2. Login with credential 3. Add a product to the cart 4. View cart 5. Fill out all the necessary fields with valid information 6. Add or reduce product from the cart"" 7. In the payment section, select pay online option" 8. Enter coupon code to avail discount |  |  | Passed

## Test Metrics
Test Metrics
SL | Metrics | Description | Result(%)
1 | Percentage of Test Case Executed | (No of Test Case Executed/Total No of Test Case written)*100 | (52/52)*100=100
2 | Percentage of Test Case Not Executed | (No of Test Cases Not Executed/Total No of Test Case Written)*100 | (0/52)*100=0
3 | Percentage of Test Case Passed | (No of Test Cases Passed/ No of Test Cases Executed)*100 | (49/52)*100=94.23
4 | Percentage of Test Case Failed | (No of Test Cases Failed/Total no of Test Cases Executed)*100 | (3/52)*100=5.77
5 | Percentage of Test Case Blocked | (No of Test Cases Blocked/ Total number of Test Case Executed)*100 | (0/52)*100=0
6 | Defect Density | No of Defects Found/Size(No of Requirements) | N/A
7 | Defect Removal Efficiency(DRE) | (Fixed Defects/(Fixed Defects+Missed Defects))*100 | N/A
8 | Defect Leakage | (No of Defects found in UAT/ No of Defects found in Testing)*100 | N/A
9 | Defect Rejection Ratio | (No of defects rejected/ Total no of defects raised)*100 | N/A
10 | Defect Age | Fixed date-Reported Date | N/A
11 | Customer Satisfaction | No of complaints per period of time | N/A

## Bug Report
Bug Report
SL No: BS-039
Issue: User cannot change password by providing valid phone number or email
Reproducing Steps:
1. Go to URL https://bionstyle.com/ 2. Hover on 'My Account' 3. Click on login 4. Click on forgot password
Env: Production
Module: Login
Responsible QA:Nusrat Jahan Mou

## Test Report
Test Report
Project Name | Bion Style
Module Name | Sign Up, Login and Place Order
Test Case Version
Written By | Nusrat Jahan Mou
Executed By | Nusrat Jahan Mou
Reviewed By
Test Execution Report | [5 empty] | Total No | Status
Test Case | Pass | Fail | Out Of Scope | Not Executed | Total TC | Pass | 49
| 49 | 3 | 0 | 0 | 52 | Fail | 3 | Result :
Grand Total | 49 | 3 | 0 | 0 | 52 | Out Of Scope | 0
[6 empty] | Not Executed | 0
LIMITATIONS | [7 empty] | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Documents |  |  | Recieved | Useful
PRD |  |  | No | No
USER STORY |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values
Yes/ No. Justification (If No): | Risked based Testing or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing. ,